## Slide 1: NYHQ DSRIP Primary Care & Behavioral Health Committee Kick-Off Meeting
March 2015

## Slide 2: Agenda
Welcome & Introductions
PPS Overview & Organizational Structure
DSRIP Updates
  Progress To Date
  Implementation Plan
Committee Purpose
Implementation Plan Draft – Review
  Revision process
Resources
Next Steps
    Implementation Plan – Final Submission (April 1, 2015)
    Next Committee Meetings

## Slide 3: PPS Organizational Structure
Executive Committee
PAC
Audit
Compliance
*Sub-Committees & Workgroups will be formed as needed.
NYHQ
Lead Hospital
Practitioner Engagement
NYHQ
Board of Directors
Cultural Comp & Health Literacy
Long Term Care
High Risk Population
Behavioral Health & Primary Care Integration
Communications
Workforce
IT & Performance Reporting
Clinical Integration & Population Health Mgmt
Finance
PMO

## Slide 4: PPS Org Structure: Committees

## Slide 5: DSRIP Updates
CNA Completed & Projects Selected –
Notes: Call to partners for any information on providers who they recommend to be involved in our PPS / Explain the recruitment process for 4th round
Attestation forms – communicate the process of how they will need to be signed

## Slide 6: DSRIP Updates
DSRIP Plan – December 2014
Scale & Speed – January 2015
Actualization of Plans –
Begin April 1, 2015
Implementation Plan – April 2015
Documents Available:
DSRIP Applications
Scale & Speed by Project
Implementation Plan Draft
Current State

## Slide 7: DSRIP Updates
Distribution Year Quarter | Reporting Period | Quarterly Report Due | Payment Date
 | Project Plan & Implementation Plan | N/A | April 20, 2015
DY1 - Q2 | April 1, 2015 - June 30, 2015 | July 31, 2015 | October 29, 2015
DY1 - Q3 | July 1, 2015 - September 30, 2015 | October 31, 2015 | April 1, 2016
DY1 Q4 | October 1, 2015 - December 31, 2015 | January 31, 2016 | 
DY2 - Q1 | January 1, 2016 - March 31, 2016 | April 30, 2016 | October 1, 2016
DY2 - Q2 | April 1, 2016 - June 30, 2016 | July 31, 2016 | 
DY2 - Q3 | July 1, 2016 - September 30, 2016 | October 31, 2016 | April 1, 2017
DY2 - Q4 | October 1, 2016 - December 31, 2016 | January 31, 2017 | 
DY3 - Q1 | January 1, 2017 - March 31, 2017 | April 30, 2017 | October 1, 2017
DY3 - Q2 | April 1, 2017 - June 30, 2017 | July 31, 2017 | 
DY3 - Q3 | July 1, 2017 - September 30, 2017 | October 31, 2017 | April 1, 2018
DY3 - Q4 | October 1, 2017 - December 31, 2017 | January 31, 2018 | 
DY4 - Q1 | January 1, 2018 - March 31, 2018 | April 30, 2018 | October 1, 2018
DY4 - Q2 | April 1, 2018 - June 30, 2018 | July 31, 2018 | 
DY4 - Q3 | July 1, 2018 - September 30, 2018 | October 31, 2018 | April 1, 2019
DY4 - Q4 | October 1, 2018 - December 31, 2018 | January 31, 2019 | 
DY5 - Q1 | January 1, 2019 - March 31, 2019 | April 30, 2019 | October 1, 2019
DY5 - Q2 | April 1, 2019 - June 30, 2019 | July 31, 2019 | 
DY5 - Q3 | July 1, 2019 - September 30, 2019 | October 31, 2019 | April 1, 2020
DY5 - Q4 | October 1, 2019 - December 31, 2019 | January 31, 2020 | 
First Due Date

## Slide 8: Committee Purpose- Planning Phase
Develop a structure for collaboration to focus on organizational functions and project implementation and outcomes specific to DSRIP deliverables according to the need of PPS partners and the community they serve. Committees will:
Refine & finalize Implementation Plans – Due April 1, 2015
  High level milestones / Risks & Mitigations / Financial Milestone Dates

## Slide 9: Committee Purpose- Operational Phase
Develop plans for actualization of functions or projects
  Project Plans
  Budgets
  Partner Expectations
Engage key-stakeholders specific to project or function need
Provide guidance for best practice standards & evidence based medicine protocols
Recommend strategies or policies to the Executive Committee
Establish monthly reporting expectations & communication channels for progress updates
Partner with PMO to monitor monthly & quarterly deliverables
Create workgroups to continue development or implementation

## Slide 10: Primary Care & Behavioral Health Projects
2.a.ii Increase Certification of Primary Care Practitioners with PCMH Certification and/or Advanced Primary Care Models (as developed under the NYS Health Innovation Plan (SHIP))
3.a.i Integration of Primary Care and Behavioral Health Services

## Slide 11: 2.a.ii Project Overview
Project 2.a.ii: Increase Certification of Primary Care Practitioners with PCMH Certification and/or Advanced Primary Care Models (as developed under the NYS Health Innovation Plan (SHIP))
Objective: This project will transform all safety net providers in primary care practices into NCQA 2014 Level 3 Patient Centered Medical Homes (PCMHs) or Advanced Primary Care Models by the end of Demonstration Year (DY) 3.
Goals:
  Initiate a rapid transformation by achieving NCQA 2014 Level 3 Patient Centered Medical Homes (PCMHs) or Advanced Primary Care Models by the end of Demonstration Year (DY) 3. Performing Provider Systems

## Slide 12: Project 2.a.ii- Risks & Mitigations
Risk 1: Aggressive speed and scale commitments
  Mitigation: Identify and leverage a PCP champion in the primary care practices to motivate and mobilize with existing practices that are at various stages of recognition to attain this level, use clinical integration strategies to align the PCPs and the PPS; and closely monitor progress to milestones and metrics
Risk 2: The level of diversity in the PPS catchment basin and the cultural challenges associated with patient engagement, health literacy and communication with providers
  Mitigation: Processes for engaging patient through outreach and navigation activities, leveraging community health workers, peers, and culturally competent community-based organizations to garner a care transition partnership with this culturally diverse population

## Slide 13: Engaged Patient Definition
2.a.ii Increase Certification of Primary Care Practitioners with PCMH Certification and/or Advanced Primary Care Models (as developed under the NYS Health Innovation Plan (SHIP)) | 
Counting Methodology: | A count of patients that meet the criteria over a 1-year measurement period. Duplicate counts of patients are not allowed. The count is not additive across DSRIP years.
Engaged Patient Definition: | The number of participating patients who receive preventative care screenings from participating providers to identify unmet medical or behavioral health needs from participating PCPs.

## Slide 14: 2.a.ii: Project Implementation Speed

## Slide 15: 2.a.ii: Patient Engagement Speed

## Slide 16: 3.a.i Project Overview
Project 3.a.i: Integration of Primary Care and Behavioral Health Services
Objective: Integration of mental health and substance abuse with primary care services to ensure coordination of care for both services.
Goals:
  Integration of behavioral health and primary care services can serve
  Care for all conditions delivered under one roof by known healthcare providers

## Slide 17: Project 3.a.i- Risks & Mitigations
Risk 1: The potential of medical based projects overshadowing and diverting focus away from behavioral health services and the transition of services into the patient care pathways
  Mitigation: the PPS will identify and empower behavioral health providers to act as liaisons and champions to the clinical integration team and to chronic care management health projects.
Risk 2: provider attitudes toward behavioral health issues and substance abuse tendencies preclude active participation and patient engagement
  Mitigation: Targeting providers in specific community settings to increase patient identification and engagement. A hybrid model for integration of primary care and behavioral health services will focus on adapting pre-existing resources to include the preventive care screening PHQ-9 and SBIRT tool with coordinated referrals so that missed opportunities are minimal

## Slide 18: Project 3.a.i- Risks & Mitigations
Risk 3: cultural stigma toward behavioral health and mental health issues for patients, families and their communities
  Mitigation: Patient, family and community education programs that link with the Cultural Competency / Health Literacy implementation plans will help to keep patients engaged after identification.

## Slide 19: Engaged Patient Definition
3.a.i Integration of Primary Care and Behavioral Health Services | 
Counting Methodology: | A count of patients that meet the criteria over a 1-year measurement period. Duplicate counts of patients are not allowed. The count is not additive across DSRIP years.
Engaged Patient Definition: | The total number of patients engaged per each of the three models in this project, including: A. PCMH Service Site: Number of patients screened (PHQ-9/SBIRT) B. Behavioral Health Site: Number of patients receiving primary care services at a participating mental health or substance abuse site C. IMPACT: Number of patients screened (PHQ-9/ SBIRT)

## Slide 20: 3.a.i: Project Implementation Speed

## Slide 21: 2.b.vii: Patient Engagement Speed

## Slide 22: Resources
NYHQ Project Management Office (PMO) –
  Maria D’Urso – mda9005@nyp.org
  Louisa Low – lil9084@nyp.org
  Crystal Cheng – crc9038@nyp.org
NYHQ PPS Website - http://www.nyhq.org/dsrippps
NYS DSRIP Website - https://www.health.ny.gov/health_care/medicaid/redesign/dsrip/
  Applications - https://www.health.ny.gov/health_care/medicaid/redesign/dsrip/pps_applications/

## Slide 23: Next Steps
Implementation Plan Revision
  Committee Feedback
  KPMG Feedback
Committee Meetings
  Additional Members
  Implementation Plan Finalization
  Actualization Planning
First Quarter Deliverable – Q2 DY1

## Slide 24
Questions?