NewYork-Presbyterian/Queens PPS

Project 3.d.ii - Pediatric Asthma Project

*Project Committee Meeting*

*March 10th, 2016 1:00pm – 2:30pm EST*

**Attendees**: J. Lavin (MHPWQ), S. McQuade (MHPWQ), A. Simmons (NYP/Q), E. Simpser (St. Mary), C. Zaiff (St. Mary) E. F-Rovato (St Mary), C. Guglielmo (ACQ), H. Jabbar (NYP/Q), M. D’Urso (NYP/Q), C. Duffy (St. Mary’s)

| **Topic** | **Discussion** | **Actions** |
| --- | --- | --- |
| 1. **Agenda:** | * Welcome & Purpose * Review & Approve Minutes * Asthma Coalition/School Based Clinic Educational Opportunities * Asthma Home Care Flow Diagram * Best Practices * Next Steps | * N/A |
| 1. **Review Minutes:**   Team | * Review and Approved Minutes from 2.9.16 Meeting | * Meeting minutes were unanimously approved. |
| 1. **Asthma Coalition/School Based Clinic Educational Opportunities:**   C. Guglielmo | * Training will be set up in city schools. * A Gap found in the school system is the referral process: Who will write the referral? * There will be training for the staff with self-management applications. * There will be Training for school Nurses. * MAP-form will be electronically available for authorization of medication in schools. | * C. Guglielmo will meet with J. Lavin next week to set up training arrangements. |
| 1. **Asthma Home Care Flow Diagram:** 2. Simmons | * Reviewed the changes and updates to the Asthma Home Care Flow Diagram from the last meeting. | * Committee unanimously approved the updated Asthma Home Care Flow Diagram. |
| 1. **Best Practices :**   H. Jabbar  C. Guglielmo | * National heart, Lung and Blood Institute’s National Asthma Education and Prevention Program. * Guidelines Implementation Panel Report for EPR-3 * Some Best Practices were discussed such as:   + 6 guidelines implementation of simple strategies   + Physician Asthma Care Program (PACE)   + Open Airways   + NEHC   + CDC check list | * + N/A |
| 1. **Next Steps & Needs**:   Team | * Implement an efficient Asthma plan on EHRs with imbedded medication drop down box. * Healthix is currently an issue due to the exclusion of children’s records ages 10-18. * Primary care providers need to be represented in the Asthma project. | * Create a focused group lunch for PCP to discuss practices, feedback, recommendations, and implementation strategies. * Dr. Simpser will meet with Healthix to address children age gap in RHIO. |