NewYork-Presbyterian/Queens PPS

Project 3.d.ii - Pediatric Asthma Project

*Project Committee Meeting*

*March 10th, 2016 1:00pm – 2:30pm EST*

**Attendees**: J. Lavin (MHPWQ), S. McQuade (MHPWQ), A. Simmons (NYP/Q), E. Simpser (St. Mary), C. Zaiff (St. Mary) E. F-Rovato (St Mary), C. Guglielmo (ACQ), H. Jabbar (NYP/Q), M. D’Urso (NYP/Q), C. Duffy (St. Mary’s)

| **Topic** | **Discussion** | **Actions** |
| --- | --- | --- |
| 1. **Agenda:**
 | * Welcome & Purpose
* Review & Approve Minutes
* Asthma Coalition/School Based Clinic Educational Opportunities
* Asthma Home Care Flow Diagram
* Best Practices
* Next Steps
 | * N/A
 |
| 1. **Review Minutes:**

Team  | * Review and Approved Minutes from 2.9.16 Meeting
 | * Meeting minutes were unanimously approved.
 |
| 1. **Asthma Coalition/School Based Clinic Educational Opportunities:**

C. Guglielmo | * Training will be set up in city schools.
* A Gap found in the school system is the referral process: Who will write the referral?
* There will be training for the staff with self-management applications.
* There will be Training for school Nurses.
* MAP-form will be electronically available for authorization of medication in schools.
 | * C. Guglielmo will meet with J. Lavin next week to set up training arrangements.
 |
| 1. **Asthma Home Care Flow Diagram:**
2. Simmons
 | * Reviewed the changes and updates to the Asthma Home Care Flow Diagram from the last meeting.
 | * Committee unanimously approved the updated Asthma Home Care Flow Diagram.
 |
| 1. **Best Practices :**

H. JabbarC. Guglielmo | * National heart, Lung and Blood Institute’s National Asthma Education and Prevention Program.
* Guidelines Implementation Panel Report for EPR-3
* Some Best Practices were discussed such as:
	+ 6 guidelines implementation of simple strategies
	+ Physician Asthma Care Program (PACE)
	+ Open Airways
	+ NEHC
	+ CDC check list
 | * + N/A
 |
| 1. **Next Steps & Needs**:

 Team | * Implement an efficient Asthma plan on EHRs with imbedded medication drop down box.
* Healthix is currently an issue due to the exclusion of children’s records ages 10-18.
* Primary care providers need to be represented in the Asthma project.
 | * Create a focused group lunch for PCP to discuss practices, feedback, recommendations, and implementation strategies.
* Dr. Simpser will meet with Healthix to address children age gap in RHIO.

  |