| Meeting Title: | NYP Queens DSRIP Asthma Home Based Care | Meeting Date: | July 11, 2017 |
| --- | --- | --- | --- |
| Facilitator(s): | H. Jabbar, MD C. Guglielmo | Meeting Time: | 2:00 pm-3:00 pm |
| Location: | NYP Queens Hospital, MRI Conference Room 1-866-692-4538 26098085# |  |  |

Meeting Purpose:

DSRIP Project Implementation – Committee meeting

| # | Topic | Responsible Person | Document |
| --- | --- | --- | --- |
| 1. | Welcome | H. Jabbar, MD | - |
| 2. | Review & Approve Minutes: 5/10/2017 | H. Jabbar, MD |  |
| 3. 4. | Actively Engaged Patients: - The PMO has met the target number for actively engaged patients for DY3.Q1which was 41 patients. The PMO is still collecting June’s data. - The target number for DY3. Q2 for actively engaged patients is 138. This metric is due at the end of September. - Claudia and St. Mary’s will collaborate with the PMO on outreach to partners who are not engaged or sending patients. - Claudia will educate new providers on the home assessment referral process. Current Status - New templates were sent out to partners with updated columns, please reach out to Renjie if there are any questions. Next Steps: - Claudia and St. Mary’s will collaborate with the PMO on an out-reach strategy to partners who are not engaged or sending patients. Quality Data Review: - Rapid Cycle evaluation data review and action planning. | H. Jabbar, MD K. Fung |  |
| 5. | DY3Q4 Deliverable: Milestone# 5: Ensure coordinated care for asthma patients includes social services and support. Metric 5.3: PPS has assembled a care coordination team that includes use of nursing staff, pharmacists, dieticians and community health workers to address lifestyle changes, medication adherence, health literacy issues, and patient self-efficacy and confidence in self-management. Next Steps: - The PMO will develop the Care Coordination roster for reporting including Peds, Asthma Center, ED, Saint Mary’s nurses. - The PMO will create a packet for pharmacist with laminated visual instructions, educational pamphlet with DSRIP referral information. - The PPS would need to engage Total Care Rx and Alexander Infusion. Minimum Documentation: Documentation of process and workflow including responsible resources at each stage of the workflow. Current Status: - Total Care Rx and Claudia need to come up with a strategy for Asthma education. - C. Duffy will confirm whether Medicaid patients have a co-pay for homecare assessment. Patient Needs: - Social services patient needs-resource and gaps. - Social services process of coordination- discussion of current processes. Current Status: - Asthma Coalition Training Progress Update- status of trainings, challenges in outreach, next wave of training. | - Simmons |  |
| 7. | Questions & Open Discussion | Team | - |
| 8. | Adjourn | - | - |