# NewYork-Presbyterian/Queens PPS

Project –HHC Project Sub-Committee

Project Committee Meeting

February 18, 2016 10:00pm – 10:30pm EST

Attendees: C. Duffy (St. Mary), C. Keane (NYPQ),P. Faye (Centerlight ), C. Jennings M. D’Urso(NYP/Q),P. Mezei (Americare) B. Gallagher (Americare), S. Kalinowski (NYP/Q),S. Gagliardi (MJHS), D. Forbes (Alpine Home Care) S. Schwartz (Revival Home care)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Purpose - Root Cause Analysis-Case Studies - INTERACT-like tools - Training - Project Requirements - Question &Discussion |  |
| - Welcome & Purpose : C. Keane | - Purpose of the meeting is to determine best practices through Rapid Cycle Evaluation, discuss INTERACT training, and Project Requirements. | - N/A |
| - Root Cause Analysis Case Studies: Team | - Rapid Cycle Evaluation - These meeting will review the cause of the readmission and do quality assurance to ensure best practices can be updated accordingly for the PPS - All cases will be anonymized prior to distribution and review - First meeting will entail education on how to perform a root cause analysis - St. Mary is concerned about children’s age and how it will affect HIPPA regulations | - Partners agreed on having a Root-Cause Analysis meeting quarterly |
| - INTERACT: Team | - INTERACT will help focus on Home Care specific educators - ST. Mary currently not using INTERACT - Americare has all nurses and MAs trained in INTERACT. - Metro Jewish had it built into their EHR. - Each partner must identify who their facility champion is and review the roles and responsibilities. | - Partners will email Sarah their identified facility champion. |
| - INTERACT Training: | - There will be 2 dates for INTERACT training that are 6 hour sessions in May and June. - A nurse Manager, Manager of Aides and housekeeping must attend the training.. | - PMO will send out INTERACT dates, locations, and times |
| - Project Requirements: S. Kalinowski | - Requirements are due by DY1,Q4 - Each partner must identify a facility champion - Each partner must educate all staff on care pathways and INTERACT principles. | - N/A |
| - Questions & Discussions | - DOH requirements for DSRIP identify what the state is looking for. | - N/A |