# NewYork-Presbyterian/Queens PPS

Project 4.c.ii – HIV Partner Collaboration

Project Committee Meeting

March 3rd, 2016 12:00pm – 1:00pm EST

Attendees: K. Francois (NYP), D Rubin (NYPQ), S Williams (Brightpoint), G JennaJohn (?) (ACQC),  M. Durso (NYPQ), R.J Hopkins (Total Care Rx)C. Jennings ((Total Care Rx), M. Hay (NYPQ) L. McConnell (NYP/Q), P. Cartmell (NYP/Q), T. McCormack (NYP/Q) C. Velasco (NYP/Q) , A. Simmons (NYP/Q), P. Fave (NYP/Q) E, Moas (ArchCare) S. Kalinowski (NYP/Q)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Introductions - Review & approve meeting minutes - Review IT & data sharing - Peer-lead intervention strategy development - Deliverables - Question &Discussion | - N/A |
| - Review & Approve meeting minutes: Dr. Rubin | - Review & Approve meeting minutes from 2.18.16 | - Team approved meeting minutes. |
| - Review IT & data sharing: M. Hay | - It Team discusses the IT & data component of the project. - SHINEY is the main database from the DOH. - The PPS can create a tracking system until SHINEY is ready. - This will help with tracking consent with the HIV population - The IT and clinicians will collaborate to meet clinicians needs to help track patient data. - IT Team Proposes All Script Care Director for the main tracking system - There are incentives involved such as meaningful use and RHIO usage. - IT would like to create an ideal model for referrals and a patient tracking system. | - PMO will send out IT presentation for partners. |
| - Peer-lead intervention strategy development: Team | - Reviewed Risk and Gaps document. - Discussed changes to the list by adding risk and Gaps such as behavioral/mental health issues among the HIV positive community. - Discussed the issues of access to HIV medications once patients are diagnosed with rapid testing. - Discussed the lack of education providers have on HIV testing state laws. - Suggestion of the training component of DSRIP could be accomplished by DOH involvement. - Focusing on providers with a high population of HIV patients - NY links is a great source to get more information because they link HIV positive individuals to care. | - Revise Risk and Gaps document to reflect additives and suggestions in the meeting. |
| - Deliverables: - Simmons | - Deliverables Milestone #2 are due 3/31/16 - Milestone #2 / Step # 1 – Identify existing peer-led intervention strategies in coordination with other PPS - Milestone #2 / Step # 2 – Develop peer-role model strategy by utilizing best practices | - Create Sub Committee to discuss Strategies to mitigate HIV diagnosis. |
| - Questions/Discussions: Team | - The Possibility of 1 database across all PPS was questioned? - IT Team posed the question “Are we going to be proactive or wait for SHINY to finish their database model? “. | - Schedule Next Meeting for Subcommittee and entire HIV Team. |