# NewYork-Presbyterian/Queens PPS

Project 4.c.ii – HIV Partner Collaboration

Project Committee Meeting

February 18, 2016 12:00pm – 1:00pm EST

Attendees: K. Francois (NYP), D Rubin (NYPQ), S Williams (Brightpoint), R Lopez (ACQC),  J. Lavin (MHPWQ),M. Durso (NYPQ), R.J Hopkins (Total Care Rx)C. Jennings ((Total Care Rx), M. Hay (NYPQ) L. McDonnel (NYP/Q), K. Philemon (Elmcor), T Pennerman (Elmcor) , A. Simmons (NYP/Q), K. Ong (NYP/Q)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Introductions - Purpose of Meeting - Review project expectations - NYS PPS HIV Collaboration - Identify current state &gap/risk of HIV care - Review IT & data sharing needs - Outline meeting schedule for ongoing implementation - Question &Discussion | - N/A |
| - Purpose of Meeting: Dr. Rubin | - Defined the purpose of DSRIP and specifically the project 4.c.ii HIV initiative with partners. - Commitment from the partners is vital for the success of this project. | - N/A |
| - Review project expectations: A. Simmons | - The Goal of project 4.c.ii is to identify HIV patients and connect them access to care. - Identify HIV Patients partners and get them into care. - There are 13 components to this project and we chose 7 out of the 13 components to work on. - They will be customized to fit patients’ needs as well as partner needs - Our immediate focus will be DY1,Q4 deliverables which are due March 31,2016 but we will strive as a team to push out to a larger vision of multiple quarters - The Partners must understand their clinical platforms and identify risk/barriers to make this project successful. | - Send out updated Project Summary with our chosen Core Components highlighted - Share community needs information specific to HIV to understand baseline of patients |
| - NYS PPS HIV Collaboration: Dr. Rubin | - Discussions of each partner’s existing clinical platform and their vision of how they could contribute to the 4.c.ii project was discussed Elmcor would like to help individuals to receive benefits and resources and provide them with career driven jobs - Elmcor offers employee training for individuals with HIV/AIDS - ACQH provides training throughout queens and offers services such as peer-training, prevention education and mental health counseling - John Lavin with Mental Health Providers of Western Queens offers Psychotherapist and behavioral health services - BrightPoint offers integrated HIV care in primary care practices with an 8% suppression rate - Total Care Rx) is a full service pharmacy that offers prescriptions and medication management coordination with patients and providers and would like to offer access to their database as they collect important information that might be helpful to care coordination overall | - N/A |
| - Risk/Gaps: | - Risk and gaps in HIV care were discussed and found tracking patients, data exchange, rapid testing, outreach, peer training, provider education to be the most prevalent | - Create risk/gaps &* mitigation strategy document for team use |
| - IT/data sharing: Dr. Ong | - The data exchange process was discussed with the partners introducing the RHIO and Infrastructures where providers, health professional, and patients can share data | - Add to upcoming agenda item |
| - Outline meeting schedule for ongoing implementation. | - The Project deadlines were discussed with 3/31/16 being the first deadline - Meetings were set for every two weeks on a Thursday - The meeting structure was encouraged to be an open forum where the partners can collaborate on ideas to make the project successful and complete deliverables outlined. | - Schedule upcoming meeting for March 3, 2016 @ 12 |