| Meeting Title: | NYP/Q DSRIP Asthma Project | Meeting Date: | March 8, 2016 |
| --- | --- | --- | --- |
| Facilitator(s): | H. Jabbar, MD C. Guglielmo | Meeting Time: | 1:00 PM – 2:30 PM |
| Location: | St. Mary’s Hospital for Children (29-01 216th St. , Bayside, NY 11360 –Rm 270 -2nd Floor) |  |  |

Meeting Purpose:

DSRIP Project Implementation – Committee meeting

| # | Topic | Responsible Person | Document |
| --- | --- | --- | --- |
| 1. | Welcome & Purpose | H. Jabbar, MD | - |
| 2. | Review & Approve Minutes | - Simmons |  |
| 3. | Asthma Coalition / School Based Clinic Educational Opportunities - Progress Updates - Next Steps - Additional Needs | C. Guglielmo | - |
| 4. | Asthma Home Care Flow Diagram – Updated | A. Simmons |  |
| 5. | Outline Best Practices based on Flow Diagram – - National Heart, Lung and Blood Institute's National Asthma Education and Prevention Program Guidelines Implementation Panel Report for EPR-3 - Other Best Practices | H. Jabbar C. Guglielmo |  |
| 6. | Define Next Steps & Needs | Team | - |

| Milestone/ Name | Status | Start Date | End Date |
| --- | --- | --- | --- |
| Task Step 1...Utilize the National Heart, Lung and Blood Institute's National Asthma Education and Prevention Program Guidelines Implementation Panel Report for EPR-3 to define the PPS best practice protocols. Ensure processes & protocols address utilization of nursing staff, pharmacists, dieticians & CHW's. | In Progress | 8/1/15 | 3/31/16 |
| Task Step 2...Review guidelines with the clinical sub-committee & the Asthma Coalition for revisions. | In Progress | 8/1/15 | 3/31/16 |
| Task Step 3...Review best practice standards & flow diagram with the Asthma Coalition & any other designated CBO's to ensure collaboration & involvement. | DY1, Q4 Report | 1/1/16 | 3/31/16 |

| 7. | Questions & Open Discussion | - | - |
| --- | --- | --- | --- |
| 8. | Adjourn | - | - |