| Meeting Title: | NYP/Q DSRIP Asthma Home Based Care | Meeting Date: | August 9, 2016 |
| --- | --- | --- | --- |
| Facilitator(s): | H. Jabbar, MD C. Guglielmo | Meeting Time: | 1:30pm – 2:30 pm |
| Location: | NYP/Queens Hospital, J.P. Conference Room Call in : 866-692-4538 code: 26098085# |  |  |

Meeting Purpose:

DSRIP Project Implementation – Committee meeting

| # | Topic | Responsible Person | Document |
| --- | --- | --- | --- |
| 1. | Welcome | H. Jabbar, MD | - |
| 2. | Review & Approve Minutes | H. Jabbar, MD |  |
| 3. | Patient Engagement - The Pediatric Asthma Center - DY2, Q2 Target | H. Jabbar, MD S.Choudhury | - |
| 4. | Educate Pediatricians about the home assessment and education project to expand PPS partners to facilitate patient engagement | H. Jabbar, MD C. Guglielmo |  |
| 4. | Home Assessment Tool/Checklist | C. Guglielmo | - |
| 5. | Milestone# 1 Expand asthma home-based self-management program to include home environmental trigger reduction, self-monitoring, medication use, and medical follow-up Task Step 5...Define partners involved by care outlined in clinical flow diagram & review operational needs for workforce, IT, and operational processes. (Due: Sep 30, 2016) Task Step 6...Utilizing the partner listing, clinical flow diagram, and best practice standards, define a timeline to align with the requirement deliverable date of DY3, Q4 as well as the expectations of scale & speed. (Due: Sep 30, 2016) | Team |  |
| 6. | Milestone# 2: Establish procedures to provide, coordinate, or link the client to resources for evidence-based trigger reduction interventions. Specifically, change the patient’s indoor environment to reduce exposure to asthma triggers such as pests, mold, and second hand smoke. Deliverable: PPS has developed intervention protocols and identified resources in the community to assist patients with needed evidence-based trigger reduction interventions. (Due: Sep 30, 2016) - Documentation of process and workflow including responsible resources at each stage of the workflow - Written training materials - List of training dates along with number of staff trained - Patient education materials | Team |  |
| 7. | Virtual Asthma Resource Center | H. Jabbar, MD Team |  |
| 8. | Milestone# 1 Expand asthma home-based self-management program to include home environmental trigger reduction, self-monitoring, medication use, and medical follow-up Task Step 7: Partner with the Cultural Competency sub-committee to include cultural competency & health literacy processes in all aspects of home care - GNYHA Cultural Competency Training - Aug 24, Sep 13, Oct 21 | S.Choudhury | - |
| 9. | Questions & Open Discussion / Next Meeting | Team | - |
| 10. | Adjourn | - | - |