# NewYork-Presbyterian/Queens PPS

Project 3.d.ii - Pediatric Asthma Project

Project Committee Meeting

Feb9ruary, 2016 12:30pm – 1:30pm EST

Attendees: J. Lavin (MHPWQ), S. McQuade (MHPWQ), A. Simmons (NYP/Q), S. Kalinowski (NYP/Q), C. Guglielmo (ACQ), H. Jabbar (NYP/Q), M. D’Urso (NYP/Q), C. Duffy (St. Mary’s)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Purpose - School Based Clinics - Asthma Home Care Flow Diagram - Best Practices - Q4 Deliverables - Questions | - N/A |
| - School Based Clinics: J. Lavin & C. Guglielmo | - Asthma Coalition will provide education to staff at these clinics to identify asthmatic children and refer to the ARC or a PCP provider for evaluation and management - Majority of sites are elementary & middle school - Students solely receive psychotherapy - Unaware of asthma rate in students at these schools - ACQ is piloting an assessment for the high school level students - Difficult for parents to accept that asthma is a chronic disease and that children take medications daily for this; still a lot of stigma around this - Goal is to have patients on controllers versus rescue inhalers - St. Mary’s offered an opportunity for “IPO” to present algorithms based on 17 years of research | - J. Lavin & S. McQuade to follow-up on availability to hold training session for staff - C. Guglielmo to follow-up with J. Lavin to define next steps and availability of training options - C. Guglielmo to include St. Mary’s in CBO/School Based Clinic discussions |
| - Care Flow Diagram: A. Simmons | - Reviewed Care Flow Diagram - Open Airways from American Lung Association is in the schools already - In PCP world, MAF takes the place of the asthma action plan - This is a huge lift per ACQ - Need to get MCOs on board with prescribing 2 inhalers- 1 for home and 1 for school - Update “School Based Clinics” box on diagram to “NYC School Health Services” with a second box of School based clinics | - A. Simmons to update & distribute diagram to team. Finalized diagram will be project deliverable - A. Simmons to discuss budget needs & identify funding for positions |
| - Best Practices: H. Jabbar, MD C. Guglielmo | - Discussions of numerous best practices - H. Jabbar and C. Guglielmo decided to review & present best practice recommendations at a future meeting | - H. Jabbar / C. Guglielmo will present best practices to an upcoming committee meeting |
| - Q4 Deliverables: A. Simmons | - Deliverables were reviewed and shared with the committee - Project is on target for Q4 deliverables | - N/A |