NewYork-Presbyterian/Queens PPS

Project 3.d.ii - Pediatric Asthma Project

*Project Committee Meeting*

*June 21st, 2016 10:45 am – 11:45am EST*

**Attendees**: C. Zaiff (St. Mary), C. Guglielmo (ACQ), H. Jabbar (NYP/Q), C. Duffy (St. Mary’s),K. Fung (NYPQ), C. Dunkley (NYPQ), J. Lavin (MHPWQ), A. Cheng (Revival )

| **Topic** | **Discussion** | **Actions** |
| --- | --- | --- |
| 1. **Agenda:**
 | * Welcome & Purpose
* Review & Approve Minutes
* Action Item Follow-Up: 4/27/16 Meeting
* School Based Education Updates
* Provider & Staff EDUCATION Program
* IT Tool Discussion :Population Health Management Tool
* Questions/Discussions
 | * N/A
 |
| 1. **Review Minutes:**
2. Simmons
 | * Review and Approved Minutes from 4.27.16 Meeting
 | * Meeting minutes were unanimously approved.
 |
| 1. **Action Item Follow-up: 4/27/16 Meeting :**

H. Jabbar | * The Committee discussed who the NYPQ educators are and who is education the ED doctors?
* The Committee suggested a lunch meeting with the ED director and doctors to present the asthma program to aid in cooperating with DSRIP.
* The Committee requested a time frame of when the PMO will release a list of the PCPs of the attributed lives in the Asthma project.
* Dr. Jabbar will be working on a portal/ database in the ED of NYPQ to track Asthma patients.
 | * Dr. Jabbar will follow up on who the educators of NYPQ are.
* The PMO will give feedback on the data release for the Asthma Committee.
 |
| 1. **School Based Education Updates:**

Claudia Guglielmo | * The Asthma Collation educated 10 city schools on Asthma.
* The state passed an initiative to enter into 30 city school with Community health workers to improve Asthma health in schools. 15 out of the 30 reside in Queens County.
* They are working on adding screens to school education throughout the summer to prepare for the fall semester.
* Claudia inquired where the workflow process of collecting data from the school and what the next steps would be.
 | * J. Lavin and C. Gugliemo will meet in the summer to discuss additional screens to be added to the education.
* PMO will follow up on feedback on workflow process of data input/output.
 |
| 1. **Provider & Staff Education Program:**

C. Guglielmo  | * Claudia sent over all training options the Asthma Coalition offers and is awaiting feedback the next steps.
* The Committee suggested an Asthma Grand Rounds to explain what the DSRIP Asthma project is about and to get providers, schools, etc engaged.
* Claudia’s Associate is holding a pediatric Meeting Guidelines for local Pediatricians and it would be a great opportunity to share our efforts on DSRIP.
 | * PMO will follow up with Claudia on Education focus group.
* PMO will look into Grand Rounds for the Asthma Project.
* PMO will inquire about Claudia’s associate to present the Asthma Project to the local pediatricians.
 |
| 1. **IT Tool Discussion : Population Health Management Tool:**

Jabbar | * Committee would like to develop a tracking tool for tracking what partners and schools have been educated.
* Claudia is currently developing an online education program that will eventually be added to Health Stream .
 | * PMO will follow up with a tracking tool to make work flow seamless to track partners and education process.
 |
| 1. **Questions/Discussion :**
 | * The Next Asthma Meeting is July 12th 2016.
 | * Next Meeting will follow up with questions presented by the committee.
 |