# NewYork-Presbyterian/Queens

Project 3.b.i- Cardiovascular

Project Committee Meeting

January 14, 2016 4:00pm – 5:00pm EST

Attendees:  M. Cartmell (NYP/Q), S. Kalinowski (NYP/Q), M. Buglino (NYP/Q), Maria D’Urso (NYP/Q), A. Somogyi, MD (NYP/Q), P. Mezi (Americare), S. Schwartz (Revival), F. Rosado (Americare), S. Williams (Brightpoint), G. Marz (NYP/Q)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: A. Somogyi, MD | - Welcome & Purpose - Approve Meeting Minutes - 5 A’s for Tobacco Cessation - Hypertension - Self-Management Goals | - N/A |
| - Meeting Minutes: A. Somogyi, MD | - Committee voted unanimously to approve the meeting minutes | - N/A |
| - 5 A’s of Tobacco Cessation: A. Somogyi, MD S. Kalinowski | - Committee reviewed the summary document - Tobacco cessation counseling is a Meaningful Use (EHR) measure - This should be an added incentive to providers - No practices are currently using the 5 A’s - Practices will begin to look at how to incorporate this into the clinical documentation (EHR or paper) - Committee voted unanimously to approve the summary & recommendations of the 5 A’s of tobacco cessation document | - N//A |
| - Hypertension: A. Somogyi, MD S. Kalinowski | - Workforce Needs - Practices need to consider who will be doing these BP checks - Standardized competency for reviewing skills - Should include competencies for manual BP check and usage of the automated system - PPS needs an algorithm for escalation based on BP reading - PPS to see if the Million Hearts Campaign has this guidance that can be utilized - Open Access Blood Pressure Checks - Process needed (may be site specific) on how to register patients & record blood pressure measurement without triggering a bill - Sites may consider holding a screening day or a health fair to allow patients from the public to have BP checked - This is not a requirement; PPS will focus on implementing this for established patients at the practices | - S. Kalinowski to send committee information on Million Hearts Campaign - S. Kalinowski, M. D’Urso & M. Cartmell to review NYP/Q BP competency and see if this can be used as a basis for standardizing across partners - P. Mezi to see if Americare has a competency that can be shared |
| - Self-Management Goals: A. Somogyi, MD S. Kalinowski | - Committee discussed parameters for self-management goals must include 2 way communication and patient understanding and acceptance of goals - Care plans can be used as a self-management goal, if appropriate based on content | - N/A |