# NewYork-Presbyterian/Queens PPS

Project –HHC Project Sub-Committee

Project Committee Meeting

March 17th, 2016 10:00pm – 10:30pm EST

Attendees: C. Duffy (St. Mary), C. Keane (NYPQ),C. Coon (VNS) M. D’Urso(NYP/Q), S. Kalinowski (NYP/Q), D. Forbes (Alpine Home Care) S. Schwartz (Revival Home care)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Purpose - Root Cause Analysis-Case - Training Needs & Coaching Program - RHIO Connectivity Status - DY1,D4 Deliverables & DY2,q1 Deliverables - Question &Discussion |  |
| - Root Cause Analysis: Team | - There will be 1-2 randomized Root Cause Analysis cases at every Quarterly meeting. - These root case analysis will help develop best practices and create learning opportunities throughout the PPS. - There will be a training session on May 20th (1 ½ hours) for Partners. - A representative from each partner preferable a Nurse Manager or nurse in the field should attend this training, - There will be an informational session in April/May. | - PMO will send out information on representative requirements. - PMO will send out invites for the May 20th training. |
| - Training Needs & Coaching Program: Team | - Partners must implement INTERACT TOOL : - The team must be trained in INTERACT - There must be proof of training - Partners should identify training needs and create a training plan for workforce. | - Partners will email PMO any training needs. |
| - RHIO Connectivity Status: | - The current state of the Partners connected to the RHO: - Revival is connected - Alphine is connected to the Bronx RHIO - VNS will follow up if they are connected with Healthix | - All Partner must be connected to RHIO. |
| - Advance Care Planning Tools: C. Keane | - The Advanced Care Planning Tools recommended by the PPS ARE INTERACT and EMOLST. - Revival is using INTERACT like tool and is looking to switch over to INTERACT. - Visiting Nursing Services is issuing INTERACT like tool called health proxy. | - Partner will follow up with Advance Care Planning Tools |
| - DY1,Q4 Deliverables & DY2,Q1 Deliverables: S. Kalinowski | - The deliverables were dispersed for Partners to review ending year 1 and anticipating year 2 to meet all the deliverables. | - N/A |