| Meeting Title: | NYP/Q DSRIP Hospital-Home Care Project Sub-Committee | Meeting Date: | April 27, 2017 |
| --- | --- | --- | --- |
| Facilitator(s): | Caroline Keane | Meeting Time: | 3:00 PM – 3:35 PM |
| Dial in #: | NYPQ Cardiovascular Conference Room Call in #1-866-692-4538 Passcode 26098085# |  |  |

Meeting Purpose:

- DSRIP Project Implementation – Milestones & Tasks

| # | Topic | Document | Responsible Person |
| --- | --- | --- | --- |
| 1. | Welcome & Purpose | - | C. Keane |
| 2. | Approve Meeting Minutes – 03/27/17 |  | C. Keane |
| 3. | Pending Receiving Some Documents from: (Please contact Coleen to get more information) - MJHS - Parker Jewish - Archcare - Self Help - Calvary |  | C. Dunkley |
| 4. | CHHA Contacts Database/Directory |  | S.Choudhury |
| 5. | Requirement for all CHHA partners to attend committee meetings |  | C. Keane |
| 6. | DY3 Tasks Tracker: (Refer to attachment to find out what we need from each CHHA) Milestone# 8: Integrate primary care, behavioral health, pharmacy, and other services into the model in order to enhance coordination of care and medication management. Metric/Deliverable: All relevant services (physical, behavioral, pharmacological) integrated into care and medication management model. Minimum Documentation: Care Coordination methodology, list of all participating services, medication management methodology ----------------------------------------------------- Milestone# 9: Utilize telehealth/telemedicine to enhance hospital-home care collaborations. Metric/Deliverable: Telehealth/telemedicine program established to provide care transition services, prevent avoidable hospital use, and increase specialty expertise of PCPs and staff. Minimum Documentation: Implementation plan; evidence of use of telemedicine services Milestone # 10: Utilize interoperable EHR to enhance communication and avoid medication errors and/or duplicative services. Metric/Deliverable: Clinical Interoperability System in place for all participating providers. Usage documented by the identified care coordinators. Minimum Documentation: HIE Systems report, if applicable; Process work flows: documentation of process and workflow including responsible resources at each stage of the workflow; other sources demonstrating implementation of the system. |  | C. Keane/ S.Choudhury C. Keane/ S.Choudhury/ M.Hay |
| 7. | Rapid Cycle Unit Overview and Linkage to Quality metrics related project deliverables Milestone #11 Measure outcomes (including quality assessment/root cause analysis of transfer) in order to identify additional interventions. Metric# 11.1: Membership of quality committee is representative of PPS staff involved in quality improvement processes and other stakeholders. --------------------------------------------------------------- Metric # 11.2: Quality committee identifies opportunities for quality improvement and use of rapid cycle improvement methodologies, develops implementation plans, and evaluates results of quality improvement initiatives. ----------------------------------------------------------------- Metric# 11.3: PPS evaluates and creates action plans based on key quality metrics, to include applicable metrics ----------------------------------------------------------------------- Metric# 11.3: Service and quality outcome measures are reported to all stakeholders. |  | S.Kalinowski/ A.Simmons C. Keane/ S.Choudhury |
| 8. | MOLST and eMOLST Training and Implementation - Identify Physician Champion at each CHHA - Identify System Champion at each CHHA |  | C. Keane |
| 9. | Questions & Open Discussion | - | C. Keane/ S.Choudhury |
| 10. | Adjourn | - | - |