# NewYork-Presbyterian/Queens PPS

Project –HHC Project Sub-Committee

Project Committee Meeting

August 4th, 2016 2:00pm – 2:4pam EST

Attendees: D. Friedman (Centerlight),C. Duffy (St. Mary), C. Keane (NYPQ), S.Choudhury (NYP/Q), P. Mezei (Americare) Pat (Centerlight ) ,W. White (VNS) K. Fung (NYPQ) C. Dunkley (NYPQ ), C. Coon (Centerlight ) Deborah (Alpine) Alex F(Americare) ,G. Difeo (VNSNY

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Purpose - Approve Meeting minutes - Root Cause Analysis-Case - INTERACT Training - Best Practices - MOLST and eMOLST Implementation Status - Project Requirement #2 Due 3/30/2017 - DY2, Q2 Deliverables - Question &Discussion | - N/A |
| - Approve Meeting minutes: Team | - Committee reviewed the minutes from 5/19/16 Meeting for approval. | - Committee unanimously reviewed and approved minutes. |
| - Root Cause Analysis Case: C. Keane | - Alpine has offered to be the next case for our first Root Cause Analysis on September 9th 10am-12pm. - Registration is currently open. | - Partner should register with PMO |
| - INTERACT Training Plan: C. Keane | - The INTERACT Training contract is currently going through legal and awaiting approval which should be completed by late October. - We are requested 2 members per facility which can be a nurse educator, champion, aid or house keeper. - The training will be an 8 hour session - St Mary’s may have a space available for training | - The PMO will update partners with further information. |
| - Best Practices Americare: | - Attached to the agenda are Americare’s best practices for heart failure. - KEYNOTE: The Physician or provider will identify a symptom that will lead to orders instead of waiting for additional orders(Standing Orders) | - The PMO will send the PPT to partners, |
| - MOLST & eMOLST: Team | - MOLST & eMOLST implementation status update: - Sunharbor is currently doing paper MOLST - Derek Murray started piloting eMOLST however are having issues with inconsistency with documenting and interfacing with EHR. “The question on the forms have raised conversation in the facility and questions they would have thought to ask “ - This is a requirement for all SNFs - The PMO is currently working on education for the eMOLST. | - Please reach out to the PMO if you need additional resources or training. |
| - Project Requirement #2 Due 3/30/2017 | Project Requirement #2 Due 3/30/2017 Ensure home care staffs have knowledge and skills to identify and respond to patient risks for readmission, as well as to support evidence-based medicine and chronic care management. - Annual Training Plan & Tracking Process - Risk Stratification - EHR Capability to Track Data - Partners must have annual trainings and must track the training with sign sheets and materials. - Each partner should pick the best practice from each facility and present it to committee. - After all partners present the committee will decide and best practices and streamline the best practices. | - Please send feedback to PMO. |
| - DY2,Q2-Q4 Deliverables : S. Choudhury | - The Committee reviewed the DY2,Q2-Q4 Deliverables to ensure the deliverables and metrics are met | - Deliverables will be attached to the agenda every meeting |