| Meeting Title: | NYP/Q DSRIP HIV Partner Collaboration Sub-Committee Project: 4.c.ii | Meeting Date: | June 2, 2016 |
| --- | --- | --- | --- |
| Facilitator(s): | Dr. David Rubin | Meeting Time: | 12:00 PM – 1:00 PM |
| Location: | NYP/Q – Room TBD 866-692-4538; 26098085# |  |  |

Meeting Purpose:

- Review project expectations - Define potential collaborations of partners among PPS - Identify future state and needs of PPS - Ensure completion of all HIV Milestones & Tasks

| # | Topic | Responsible Person |
| --- | --- | --- |
| 1. | Welcome & Introductions | Dr. Rubin |
| 2. | Review & approve meeting minutes from 4/7/16 | Dr. Rubin |
| 3. | HIV High-need Population Mapping | Amanda |
| 4. | Identify Training Needs – PPS Training Strategy - Providers - Workforce - CBO’s - Etc. | Team |
| 5. | NYS DSRIP HIV Coalition Sub-Committee Volunteers | Amanda/Dr. Rubin |
| 6. | REMINDER: DY2 Q1 & Q2 Deliverables | Amanda |

| Category | Project # / Org Unit | Rqmt Category | Unique Rqmt # | Milestone/ Name | Status | End Date | DY, Q |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Requirement | 4.c.ii | Milestone | 114 | Milestone 2. Increase peer-led interventions around HIV care navigation, testing, and other services. | In Progress | 9/30/16 | DY2, Q2 |
| Project Requirement | 4.c.ii | Step | 114d | Task Step 4...Evaluate practices on a quarterly basis | Not Started | 9/30/16 | DY2, Q2 |
| Project Requirement | 4.c.ii | Step | 115a | Task Step 1...Partner with DOH, Brightpoint Health and ACQC, CBO to create a map of high-need populations | Not Started | 6/30/16 | DY2, Q1 |
| Project Requirement | 4.c.ii | Step | 115b | Task Step 2...Utilize cross PPS work-group to develop a plan for outreach | Not Started | 6/1/16 | DY2, Q1 |
| Project Requirement | 4.c.ii | Step | 115c | Task Step 3. Present plan to clinical committee for approval | Not Started | 9/30/16 | DY2, Q2 |
| Project Requirement | 4.c.ii | Step | 116a | Task Step 1...Work with QCCP Health Home and DOH to identify the two most prevalent factors in the PPS catchment area | Not Started | 7/31/16 | DY2, Q2 |
| Project Requirement | 4.c.ii | Step | 118c | Task Step 3. Present plan to clinical committee for approval | Not Started | 5/31/16 | DY2, Q1 |
| Project Requirement | 4.c.ii | Step | 119a | Task Step 1...Utilize cross PPS work-group to develop a plan for outreach | Not Started | 6/30/16 | DY2, Q1 |

| 7. | Questions & Open Discussion | All |
| --- | --- | --- |
| 8. | Adjourn | - |