# NewYork-Presbyterian/Queens PPS

Project 4.c.ii – HIV Partner Collaboration

Project Committee Meeting

June 2nd 2016 1:30pm – 2:30pm EST

Attendees: K. Francois (NYP), D Rubin (NYPQ), S Williams (Brightpoint), R Lopez (ACQC),  R.J Hopkins (Total Care Rx)C. Jennings ((Total Care Rx),L  McConnel (NYP/Q), K. Philemon (Elmcor), T Pennerman (Elmcor) , A. Simmons (NYP/Q), C. Velasco (NYP/Q) , C. Dunkley (NYPQ), S. Kalinowski (NYPQ) , M. Hay (NYPQ)C. Velasco (NYPQ)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Introductions - Review & Approve Meeting minutes - HIV High-need Population Mapping - Identify Training Needs - NYS DSRIP HIV Outreach Coalition Sub-Committee Volunteers - Reminder : DY2 Q2 & Q2 Deliverables - Question and Open discussions | - N/A |
| - Review Meeting minutes: Dr. Rubin | - Review Meeting minutes from 4/7/116 | - Committee unanimously approved meeting minutes. |
| - HIV High-need Population Mapping: A. Simmons | - The PMO has created a high need population mapping to target the high needs areas in queens. The best returns on investments are Long Island City, Jamaica and the Rockaways. - Some Focus Groups that should be targeted at NYPQ are the Asian employees, providers, and patients. The LGBT community which will includes training on the LGBT culture such as gender neutral bathrooms. - The committee discuss the expansion of NYPQ and how to make HIV testing apart of PCP efforts in a seamlessly workflow process. | - Committee must review the strategy document and send PMO feedback. |
| - Identify Training Needs : Team | - If there are training needs from Providers, workforce, CBOs, etc please let the PMO know so we can assist with closing gaps and seeking training for each Partners, | - Partners please contact the PMO with Training needs. |
| - NYS DSRIP HIV Outreach Coalition : Team | - The DOH has standing sub-committees that each partner can contribute to on behalf of the NYPQ PPS. | - The committee will review and email the PMO with the sub-committee they are interested in. |
| - Reminder : DY2 Q2 & Q2 Deliverables: Amanda | - Embedded in the agenda the PMO has provided the committee with the deliverables for DY2, Q1 and DY2 Q2. |  |