# NewYork-Presbyterian/Queens PPS

Project 4.c.ii – HIV Partner Collaboration

Project Committee Meeting

April 7th, 2016 12:30pm – 1:30pm EST

Attendees: K. Francois (NYP), D Rubin (NYPQ), S Williams (Brightpoint), R Lopez (ACQC),  R.J Hopkins (Total Care Rx)C. Jennings ((Total Care Rx),  McDonnel (NYP/Q), K. Philemon (Elmcor), T Pennerman (Elmcor) , A. Simmons (NYP/Q), C. Velasco (NYP/Q)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Introductions - Review & Approve Meeting minutes - HIV Outreach Strategy Document - Peer Led Intervention Existing Process - DY2 Q1 & Q2 Deliverables - Question and Open discussions | - N/A |
| - Review Meeting minutes: Dr. Rubin | - Review Meeting minutes from 4/7/116 | - Committee unanimously approved meeting minutes. |
| - HIV Outreach Strategy Document: A. Simmons | - The HIV Outreach strategy is comprised of strategies from ACQC and Bright point resources to mitigate HIV incidences. - There is a need for expansion to the document of other partners such as NYPQ and Elmcor. - The strategy needs a Workflow plan for partners and providers in the PPS. | - Committee must review the strategy document and send PMO feedback. |
| - Peer Led Intervention Existing Process : Team | - Committee reviewed existing outreach strategies used in their organizations. - Dr Rubin agrees with there is no need for expansion to other partners. - Committee discussed way to increase workflow and communication between partners. - There should be an elderly outreach added to outreach strategy - Committee suggested State assistance to mandate HIV testing - Queens County Medical Society - A newsletter with all the PPS updates and information can be comprised collectively. - ACQC can upload their event calendar unto the PPS website. - ACQC can host events at partnering locations. - Committee will work from current state towards target state. - PMO could create a glossary or index with all partners in the PPS for resource purposes. - ACQC and Elmcor can educate partners and community on Cultural competency and behavioral community providers. - A Gap found was undocumented patients. | - Committee will reviews the document and email PMO edits due by April 25th. - PMO will follow up with ACQC on list of venues they would like to test. |
| - Dy2 Q1 & Q2 Deliverables: Team | - Committee reviewed deliverables for the current quarter and Q2. | - N/A |
| - Questions & Discussion: Team | - April 11th LOUD Latina at Jewish center in Jackson Heights. | - N/A |