# NewYork-Presbyterian/Queens PPS

Project 2.a.ii & 3.b.i – PCMH & Cardiovascular Project

Project Committee Meeting

June 9th, 2016 4:00pm – 5:00pm EST

Attendees: P. Cartmell (NYP/Q), M. Buglino (NYP/Q), S. Williams (Brightpoint), Donna (NYP/Q) K. Fung (NYPQ/Q) , S. Choudhury (NYP/Q), M. D’Urso (NYP/Q), A. Somogyi (NYP/Q) C. Dunkley

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Purpose - Meeting minutes Approval - 5 As - Care Coordination Teams - BP Competencies - Walk-in BP Checks - Care Plans & Self –Management Goals - Project Metrics | - N/A |
| - Meeting minutes: A. Somogyi, M.D | - Committee reviewed meeting minutes from 04/09/16 meeting. | - Committee voted to unanimously approve the meeting minutes |
| - 5 As: Committee Members | - The Committee reviewed the status of the 5 A’s implementation with Partners. - NYP/Q is using Athena and documenting the implementation in the patient’s record.. - The PMO will be making calls to Audit tracking in the Partners. | - PMO will be calling partners to audit the partners’ implementing of 5 As. /Best Practices. |
| - Care Coordination: Committee Members | - The Partners have signed up for GNYHA’s Care Coordination on June 15th. - The goal of care coordination team is to use care plans in ETW. - So partners have the Care coordination to full fill the DSRIP requirements? Are there substitutes available? - Committee reviewed how other organization would incorporate a pharmacist in their workflow. - Total Care Rx is active with the PPS and other PPS have been using pharmacy students to aid. - The Care coordination Team implementation is due by March 2017, | - PMO will inquire how other PPS are forming care coordination teams. |
| - BP Competencies/Walk-in BP: Committee Members | - The Committee received BP implementation within the partners. - The committee should bring any implementation problems to the PMO and the PMO will provide resources if needed. - Partners will be asked to report to the PPS Quarterly. | - Partners please provide PMO with feedback. |
| - Care Plans & Self –Management Goals: Committee Members | - The Committee reviewed the use of care plans for self-management goals. - NYP/Q next phase will be to build it into the EMR-ETW. - Bright point was trained on how to use care plans in ETW. | - Brightpoint will share an example of their care plans. - Partner should send out issues/risk to the PMO. |
| - Project Metrics: K. Fung | - K. Fung shared data with the committee regarding the project Metrics. - For Avoidable Readmission, Potential Preventable ED Visit, and Pediatric Composite the PCMH project is not on target. - In the Cardiovascular Project Hypertension is off target and Angina without Procedure is on target. - More Metrics will be released by the DOH in the near future. | - The DOH will release new metrics in the near future. - The PMO will work on collecting data to target the principle diagnosis of these patients. |