**NewYork-Presbyterian/Queens PPS**

Project 2.a.ii & 3.b.i – PCMH & Cardiovascular Project

*Project Committee Meeting*

*June 9th, 2016 4:00pm – 5:00pm EST*

**Attendees**: P. Cartmell (NYP/Q), M. Buglino (NYP/Q), S. Williams (Brightpoint), Donna (NYP/Q) K. Fung (NYPQ/Q) , S. Choudhury (NYP/Q), M. D’Urso (NYP/Q), A. Somogyi (NYP/Q) C. Dunkley

| **Topic** | **Discussion** | **Actions** |
| --- | --- | --- |
| 1. **Agenda:** | * Welcome & Purpose * Meeting minutes Approval * 5 As * Care Coordination Teams * BP Competencies * Walk-in BP Checks * Care Plans & Self –Management Goals * Project Metrics | * N/A |
| 1. **Meeting minutes:**   A. Somogyi, M.D | * Committee reviewed meeting minutes from 04/09/16 meeting. | * Committee voted to unanimously approve the meeting minutes |
| 1. **5 As:**   Committee  Members | * The Committee reviewed the status of the 5 A’s implementation with Partners. * NYP/Q is using Athena and documenting the implementation in the patient’s record.. * The PMO will be making calls to Audit tracking in the Partners. | * PMO will be calling partners to audit the partners’ implementing of 5 As. /Best Practices. |
| 1. **Care Coordination:**   Committee  Members | * The Partners have signed up for GNYHA’s Care Coordination on June 15th. * The goal of care coordination team is to use care plans in ETW. * So partners have the Care coordination to full fill the DSRIP requirements? Are there substitutes available? * Committee reviewed how other organization would incorporate a pharmacist in their workflow. * Total Care Rx is active with the PPS and other PPS have been using pharmacy students to aid. * The Care coordination Team implementation is due by March 2017, | * PMO will inquire how other PPS are forming care coordination teams. |
| 1. **BP Competencies/Walk-in BP:**   Committee  Members | * The Committee received BP implementation within the partners. * The committee should bring any implementation problems to the PMO and the PMO will provide resources if needed. * Partners will be asked to report to the PPS Quarterly. | * Partners please provide PMO with feedback. |
| 1. **Care Plans & Self –Management Goals:**   Committee Members | * The Committee reviewed the use of care plans for self-management goals. * NYP/Q next phase will be to build it into the EMR-ETW. * Bright point was trained on how to use care plans in ETW. | * Brightpoint will share an example of their care plans. * Partner should send out issues/risk to the PMO. |
| 1. **Project Metrics:**   K. Fung | * K. Fung shared data with the committee regarding the project Metrics. * For Avoidable Readmission, Potential Preventable ED Visit, and Pediatric Composite the PCMH project is not on target. * In the Cardiovascular Project Hypertension is off target and Angina without Procedure is on target. * More Metrics will be released by the DOH in the near future. | * The DOH will release new metrics in the near future. * The PMO will work on collecting data to target the principle diagnosis of these patients. |