**NewYork-Presbyterian/Queens PPS**

Project 2.a.ii & 3.b.i – PCMH & Cardiovascular Project

*Project Committee Meeting*

*June 9th, 2016 4:00pm – 5:00pm EST*

**Attendees**: P. Cartmell (NYP/Q), M. Buglino (NYP/Q), S. Williams (Brightpoint), Donna (NYP/Q) K. Fung (NYPQ/Q) , S. Choudhury (NYP/Q), M. D’Urso (NYP/Q), A. Somogyi (NYP/Q) C. Dunkley

| **Topic** | **Discussion**  | **Actions** |
| --- | --- | --- |
| 1. **Agenda:**
 | * Welcome & Purpose
* Meeting minutes Approval
* 5 As
* Care Coordination Teams
* BP Competencies
* Walk-in BP Checks
* Care Plans & Self –Management Goals
* Project Metrics
 | * N/A
 |
| 1. **Meeting minutes:**

A. Somogyi, M.D | * Committee reviewed meeting minutes from 04/09/16 meeting.
 | * Committee voted to unanimously approve the meeting minutes
 |
| 1. **5 As:**

Committee Members | * The Committee reviewed the status of the 5 A’s implementation with Partners.
* NYP/Q is using Athena and documenting the implementation in the patient’s record..
* The PMO will be making calls to Audit tracking in the Partners.
 | * PMO will be calling partners to audit the partners’ implementing of 5 As. /Best Practices.
 |
| 1. **Care Coordination:**

Committee Members | * The Partners have signed up for GNYHA’s Care Coordination on June 15th.
* The goal of care coordination team is to use care plans in ETW.
* So partners have the Care coordination to full fill the DSRIP requirements? Are there substitutes available?
* Committee reviewed how other organization would incorporate a pharmacist in their workflow.
* Total Care Rx is active with the PPS and other PPS have been using pharmacy students to aid.
* The Care coordination Team implementation is due by March 2017,
 | * PMO will inquire how other PPS are forming care coordination teams.
 |
| 1. **BP Competencies/Walk-in BP:**

CommitteeMembers | * The Committee received BP implementation within the partners.
* The committee should bring any implementation problems to the PMO and the PMO will provide resources if needed.
* Partners will be asked to report to the PPS Quarterly.
 | * Partners please provide PMO with feedback.
 |
| 1. **Care Plans & Self –Management Goals:**

Committee Members  | * The Committee reviewed the use of care plans for self-management goals.
* NYP/Q next phase will be to build it into the EMR-ETW.
* Bright point was trained on how to use care plans in ETW.
 | * Brightpoint will share an example of their care plans.
* Partner should send out issues/risk to the PMO.
 |
| 1. **Project Metrics:**

K. Fung  | * K. Fung shared data with the committee regarding the project Metrics.
* For Avoidable Readmission, Potential Preventable ED Visit, and Pediatric Composite the PCMH project is not on target.
* In the Cardiovascular Project Hypertension is off target and Angina without Procedure is on target.
* More Metrics will be released by the DOH in the near future.
 | * The DOH will release new metrics in the near future.
* The PMO will work on collecting data to target the principle diagnosis of these patients.
 |