| Meeting Title: | NYP Queens DSRIP Palliative Care Project Sub-Committee | Meeting Date: | April 27, 2017 |
| --- | --- | --- | --- |
| Facilitator(s): | Caroline Keane & Cynthia Pan, M.D | Meeting Time: | 3:35 PM – 4:05 PM |
| Conference Room: | NYPQ Cardiovascular Conference Room Call in : 1-866-692-4538 Passcode: 26098085# |  |  |

Meeting Purpose:

DSRIP Project Implementation

| # | Topic | Document | Responsible Person |
| --- | --- | --- | --- |
| 1. | Welcome & Purpose | - | C. Keane C. Pan, M.D. |
| 2. | Approve Meeting Minutes – 03/27/17 |  | C. Keane |
| 3. | SNF Contacts Database/Directory |  | S.Choudhury |
| 4. | Requirement for all palliative care project partners to attend committee meetings |  | C. Keane |
| 5. | What hospice programs (outside of their own programs) are the SNFs utilizing? We need list so we can consider adding them in partner network if needed |  | C. Keane/ S.Choudhury |
| 6. | EPEC - Next session: Wednesday May 10, 20177 at LICC - Survey results : Main EPEC modules that need to be made up are; - Plenary 1 & 2: Gaps in End -of-Life Care & Legal Issues - Modules 1 & 2 : Advance Care Planning & Communicating Bad News - Modules 3 & 4 : Whole Patient Assessment & Pain Management Suggestion for future topics: - Pediatric Palliative Care |  | C.Pan |
| 7. | DY3 Task Tracker for SNFs and Hospices: Milestone# 1: Integrate Palliative Care into practice model of participating Nursing Homes. Metric/Deliverable: PPS has integrated palliative care into Nursing Homes in alignment with project requirements. Minimum Documentation: Agreements with SNFs committing to integrate Palliative Care into the practice model. ------------------------------------------------------------------- Milestone# 2: Contract or develop partnerships with community and provider resources, including Hospice, to bring the palliative care supports and services into the nursing home. Metric/Deliverable: The PPS has developed partnerships with community and provider resources including Hospice to bring the palliative care supports and services into the nursing home. Minimum Documentation: Agreements between the PPS and community and provider resources including Hospice. |  | C.Keane/ S.Choudhury |
| 8. | PCOS Scale Utilization- Feedback |  | C.Keane/ S.Choudhury |
| 9. | MOLST and eMOLST Training and Implementation - Identify Physician Champion at each SNF - Identify System Champion at each SNF |  | C. Keane/ C.Pan |
| 10. | Next meeting of the HPCANYS-CAPC DSRIP Palliative Care Project Forum will take place on Tuesday, May 9, 2017 from 12:30-2:00pm. Speaker: Patricia Bomba, MD, FACP, from Excellus BlueCross BlueShield. Dr. Bomba will be discussing the eMOLST, including the value it provides and how it can be incorporated into workflow redesign. There will also be time set aside to discuss 3.g implementation thus far. This meeting is free and open to all. |  | C.Keane/ C.Pan |
| 11. | Next Month Committee Meeting- Guest speakers from Ozanam Hall to share best practices on how they transitioned from short term to long term palliative care |  | C. Keane |
| 12. | Questions & Open Discussion | - | C. Keane/ S.Choudhury |
| 13. | Adjourn | - | - |