# NewYork-Presbyterian/Queens PPS

Project –Palliative Care Sub-Committee

Project Committee Meeting

May 19th, 2016 11:00am – 11:30am EST

Attendees: C. Keane (NYPQ), C. Duffy (St. Mary ) S. Kalinowski (NYP/Q), C. Pan (NYP/Q), Mary Ann (St. Marys) Adina (Union Plaza) J (QBEC) ,S.Shuman (Parker Jewish) ,C. Pan (NYPQ) K. Fung (NYPQ) C. Dunkley (NYPQ ) ,E. Frankel (Parker Jewish )

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Purpose - Approve Meeting Minutes - EPEC Training schedule & Registration update - Palliative Care Outcome Scale - MOLST & eMOLST - Engaged Patient - DY2,Q1 and DY2,Q2 - Questions/Discussion | - N/A |
| - Approve Meeting minutes: Team | - Committee reviewed meeting minutes from 4/21/16 meeting. | - Committee voted to unanimously approve the meeting minutes. |
| - EPEC Training Schedule & Registration: C. Pan | - Dr. Pan reported the EPEC session was a success the partner were very engaged. - EPEC registration forms will be administered to the partners and need to be sent to the PMO. - Upon completing all sessions each attendee will be EPEC certified. | - Partners must send PMO registration forms with attendees. |
| - Palliative Care Outcome Scale: C. Keane C. Pan | - The Palliative Care outcome must be administered to palliative patients to achieve AV . - Committee must decide to use patient administered or staff administered version. - If staff administered will a CNA ,Nurse or social worker administer it - How often will it be administered to patients - Do Staff need to be trained on how to fill out these forms? | - Partners will email the PMO feedback. - Union Plaza has offered to do a pilot for the PPS |
| - MOLST & eMOLST: Committee | - NYPQ has installed a link in the Emolst on Allscripts - St. Mary’s is currently using MOLST on paper. - Many partners are concerned that is time consuming. - QBEC is currently using MOLST on paper. - The Committee was concerned if they use eMOLST it may not be compatible with another hospital or facility that is using paper MOLST. | - Partner should send the status to the PMO as well as any training needs. |
| - Enagaged Patients : S. Kalinowski | - Dy2 Began April 1st 2016 therefore partners must send in engaged Patients to the PMO. - Any patient who receives palliative care can be reported regardless if they were reported in dy1 if they are still receiving care. | - Partner should send engaged patients to the Data Analyst. |
| - DY2,Q1 and DY2,Q2: S. Kalinowski | - Please email Palliative Care Champions to Coleen (cod9034@nyp.org) by 6/3/16. - The Committee reviewed the DY1,Q4 & DY2,Q1 Deliverables to ensure the deliverables and metrics are met | - Partner should email Palliatve Care Champion to PMO. |