# NewYork-Presbyterian/Queens PPS

Project –SNF Project Sub-Committee

Project Committee Meeting

September 8th, 2016 3:30pm – 4:15pm EST

Attendees: C. Keane (NYP/Q) C. Dunkley(NYP/Q),  S. Choudhury(NYP/Q),  C. Duffy (St. Mary’s) D. Friedman (Margaret Tietz/Centerlight ), M. Tretola(Silvercrest) J. Berelowski (QBEC)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Introductions - Approve Meeting minutes - RCA Meeting - CAPC Online courses - SNF Partner Quality Measures - INTERACT Training Plan - Project INTERACT Milestone #6 - MOLST & eMOLST Implementation - Cureatr rollout to SNF |  |
| - Approve Meeting minutes C. Keane | - Committee reviewed meeting minutes from 08/04/16 meeting. | - Committee voted to unanimously approve the meeting minutes |
| - RCA Meeting C. Keane | - The RCA Meeting will be held tomorrow, Friday September 9th from 10 am -11:30 am at NYPQ. | - Please send registration forms to PMO. |
| - CAPC Online courses: C. Keane/ S. Choudhury | - The PMO will pay for two member of each facility to have access to CAPAC online courses. - We will do an education on how to access the modules as needed. - Please document proof of attendance (sign –in sheet or certificate) - CME credits are eligible for these courses. | - Please send attendees to PMO. |
| - SNF Partner Quality Measures: C. Keane/ S. Choudhury | - The PMO has provided a benchmark spreadsheet for all PPS SNF partners to establish taskforce plans, and implement and monitor process improvement strategies. | - Please contact the PMO for additional questions. |
| - INTERACT Training Plan: C. Keane | - The INTERACT Training contract is currently going through legal and awaiting approval which should be completed by late October. - We are requested 2 members per facility which can be a nurse educator, champion, aid or house keeper. - The training will be an 8 hour 2 day session. - We will need the partner to create an implementation tracker to have this deliverable completed by March 2017. | - Please send attendees to the PMO. |
| - Project INTERACT success: M. Tretola | - Mike Tretola showed a power point on Silvercrest’s success story on their implementation system. - Mike Tretola reported SBAR give the physician confidence to give nurses orders when they are absent. | - N/A |
| - MOLST & eMOLST: Team | - The PMO is currently rolling out INTERACT first then will follow up with MOLST and eMOLST Training. | - N/A |
| - Cureatr Rollout out SNF: S. Choudhury | - The PMO is currently rolling out the use of Cureatr in the PPS SNF partners. | - If there are any questions or concerns regarding the RHIO please reach out to Marlon Hay. |