# NewYork-Presbyterian/Queens PPS

Project –SNF Project Sub-Committee

Project Committee Meeting

March 17th, 2016 10:30pm – 11:00pm EST

Attendees: C. Keane (NY/PQ), E. Lachancy (Dry Harber), J Maware (QBEC), K. Wilshire (Elmshurst), J Garramone (NYCRN),B. O’Hra (Chapin), S. Kalinowski (NYP/Q) R. Sherman (Pavilion at Queens), S. Schumann (Parker Jewish)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Introductions - Approve Meeting minutes - INTERACT Questionnaire - Transition of Care/Record - DY1, Q4 & DY2, Q1 Deliverables - Question &Discussion |  |
| - Approve Meeting minutes C. Keane | - Committee reviewed meeting minutes from 02/18/16 meeting. | - Committee voted to unanimously approve the meeting minutes |
| - INTERACT Questionnaire: C. Keane S. Kalinowski | - There will be INTERACT Training sessions in May and June. - There were no responses from the following : INTERACT Questionnaire No Response from: - Centerlight - Centers Health Care - Chapin Home for Aging - Cliffside Rehab - Cypress Garden - Fairview Nursing; - Holliswood - Long Island Care Center - Margaret Tietz - Meadow Park - The Grand at Queens - Waterview - Woodcrest - Forest Hills. - Partners listed need to complete the Interact Questionnaire and submit to the PMO. | - Partner will send your physician champions to the PMO. - Partners will submit the INTERACT Questionnaire to PMO |
| - Transition of Care/Record: C. Keane | - The NYS Transitions of Care form will be reviewed by all Partners - Transition forms that are currently used by Partners will be reviewed. | - Partner must email the PMO feedback on the forms listed in the agenda. |
| - DY1, Q4 & DY2, Q1 Deliverables: S. Kalinowski | - Reviewed the Deliverables for Year 1 and future Year 2 deliverables. - Deliverables will be made available in advance to ensure the deadlines for each metric is met. - Partners will send out a list of engaged patients. | - Partners will send out a list of engaged patients to PMO. |
| - Questions & Discussions C. Keane | - N/A | - N/A |