**NewYork-Presbyterian/Queens PPS**

Project –SNF Project Sub-Committee

*Project Committee Meeting*

*April 21st, 2016 10:30pm – 11:00pm EST*

**Attendees**: C. Keane (NY/PQ), E. Lachancy (Dry Harbor), J Maware (QBEC), K. Wilshire (Elmhurst), J Garramone (NYCRN),C. Dunkley(NYP/Q) R. Sherman (Pavilion at Queens), S. Schumann (Parker Jewish) C. Duffy (St. Mary’s) D. Friedman (Dry Harbor ) Lorraine (Parker Jewish )

| **Topic** | **Discussion** | **Actions** |
| --- | --- | --- |
| 1. **Agenda:** | * Welcome & Introductions * Approve Meeting minutes * Milestones * INTERACT Questionnaire * Telehealth presentation * Question &Discussion |  |
| 1. **Approve Meeting minutes**   C. Keane | * Committee reviewed meeting minutes from 03/17/16 meeting. | * Committee voted to unanimously approve the meeting minutes |
| 1. **INTERACT Questionnaire:**   C. Keane  S. Kalinowski | * There will be INTERACT Training sessions in May and June. * There were no responses from the following :  |  |  | | --- | --- | | INTERACT Questionnaire  **No Response from:**   * Centerlight * Centers Health Care * Chapin Home for Aging * Cliffside Rehab * Cypress Garden * Fairview Nursing | * Holliswood * Long Island Care Center * Margaret Tietz * Meadow Park * The Grand at Queens * Waterview * Woodcrest * Forest Hills | | * Partner will send your physician champions to the PMO. * Partners will submit the INTERACT Questionnaire to PMO * Partners listed need to complete the Interact Questionnaire and submit to the PMO. |
| 1. **Telehealth Presentation:**   Station M.D  M. Kaufman | * Station MD presented a telehealth form of treatment they created to the Committee. * 50% of Readmission and transfers reduced in their 3 month pilot. * 17% of readmissions and transfers reduced in their premature pilot * 66% of transfers reduced in cerebral palsy association.   + Nurses felt more engaged in this process. | * PMO will send out Station MD Telehealth presentation. * Committee can contact M. Kaufman for further details on their telehealth project. |