NewYork-Presbyterian/Queens PPS

Project 3.d.ii - Pediatric Asthma Project

*Project Committee Meeting*

*May 10th, 2017 1:00pam – 2:00 pm EST*

**Attendees**: H. Jabbar (NYP/Q), C. Dunkley (NYPQ) , C. Duffy (St. Marys), S. Choudhury (NYPQ), R. Zhu (NYPQ) M. Hay (NYPQ), J. Lavin (MHPWQ), C. Gugliemo (Asthma Coalition ), (NYPQ), A. Simmons (NYPQ) , M. D’Urso (NYPQ), Jennifer (Advanced Pediatrics), G. Sabagol (Advanced Pediatrics ), J. Lavin (MHPWQ), S. Kalinsowki (NYPQ)

| **Topic** | **Discussion** | **Actions** |
| --- | --- | --- |
| 1. **Agenda:**
 | * Welcome & Purpose
* Review & Approve Minutes
* Actively Engaged Patient Goals-Mitigation Strategy
* Future Deliverables
* Rapid Cycle
* Questions/Discussions
 | * N/A
 |
| 1. **Review Minutes:**

H. Jabbar  | * Review and Approved Minutes from 4.12.17 Meeting.
 | * Meeting minutes were unanimously approved .
 |
| 1. **Actively Engaged Patient Goals-Mitigation Strategy**
2. Gugliemo

 | * Update to Actively engaged definition: Any patient that is referred to home care assessment
* Include two more columns in the actively engaged templates: Refer to and Home Assessment completion date. In efforts to improve tracking the actively engaged.
* Are any providers reporting to other Home Cares than St. Mary’s?
	+ Claudia will educate any new providers; the PMO can provide the information.
* St. Mary’s is closing the loop on completed Home Care Assessments to Dr. Sabagol.
* PMO can send weekly provider emails to the partners and Claudia can help with email descriptions and reminders.
* Claudia and St. Mary’s can collaborate with PMO on outreach to partners who are not engaged or sending patients.
* Claudia and Caroline will coordinate for the conversation on ED patient navigator work.
 | * New templates were sent out to partners yesterday with updated columns, please reach out to Renjie if there are any questions.
* Claudia and St. Mary’s can collaborate with PMO on outreach to partners who are not engaged or sending patients.
* S. Choudhury will start the introductions for C. Gugliemo and C. Kean on ED patient navigatior work.
 |
| 1. **DY3Q4 Deliverables:**

S. Choudhury/Team  | * Metric 5.3
* PMO will develop the Care coordination Roster for reporting including Peds Asthma Center, ED, Saint Mary’s nurses.
* The PPS would need to engage pharmacist from the serving areas like Jackson Heights.
* A current pharmacy partner is Total Care Rx , in- house pharmacy, and Alexander Infusion.
* Create packet for pharmacist from DSRIP to provide to for their patients with laminated visual instructions, educational pamphlet with DSRIP referral information.
* Is there a co-pay for Homecare Visit?
 | * Total Care Rx and Claudia would have a conversation on Asthma education.
* C. Duffy will confirm whether Medicaid patients have a co-pay for homecare assessment.

  |
| 1. **Questions/ Discussion: Team**
 | * If partners are interested in Cureatr M. Hay can set up notifications with partners to be alerted when patients hit the ED.
* Partner would have to submit their patient registry to be uploaded into system.
* M. Hay and partners will work on configuring the tool.
* H. Jabbar reported out the Education Resource Center is coming to fruition very soon and Nurses are going to be coming to educate patients.
* C. Gugliemo and H. Jabbar are reviewing education tools and resources for the Education Resource Center.
 | * Please contact M. Hay for further information.
 |