# NewYork-Presbyterian/Queens PPS

Project 3.d.ii - Pediatric Asthma Project

Project Committee Meeting

May 10th, 2017 1:00pam – 2:00 pm EST

Attendees:  H. Jabbar (NYP/Q), C. Dunkley (NYPQ) , C. Duffy (St. Marys), S. Choudhury (NYPQ), R. Zhu (NYPQ)  M. Hay (NYPQ), J. Lavin (MHPWQ), C. Gugliemo (Asthma Coalition ), (NYPQ), A. Simmons (NYPQ) , M. D’Urso (NYPQ), Jennifer (Advanced Pediatrics), G. Sabagol (Advanced Pediatrics ), J. Lavin (MHPWQ), S. Kalinsowki (NYPQ)

| Topic | Discussion | Actions |
| --- | --- | --- |
| - Agenda: | - Welcome & Purpose - Review & Approve Minutes - Actively Engaged Patient Goals-Mitigation Strategy - Future Deliverables - Rapid Cycle - Questions/Discussions | - N/A |
| - Review Minutes: H. Jabbar | - Review and Approved Minutes from 4.12.17 Meeting. | - Meeting minutes were unanimously approved . |
| - Actively Engaged Patient Goals-Mitigation Strategy - Gugliemo | - Update to Actively engaged definition: Any patient that is referred to home care assessment - Include two more columns in the actively engaged templates: Refer to and Home Assessment completion date. In efforts to improve tracking the actively engaged. - Are any providers reporting to other Home Cares than St. Mary’s? - Claudia will educate any new providers; the PMO can provide the information. - St. Mary’s is closing the loop on completed Home Care Assessments to Dr. Sabagol. - PMO can send weekly provider emails to the partners and Claudia can help with email descriptions and reminders. - Claudia and St. Mary’s can collaborate with PMO on outreach to partners who are not engaged or sending patients. - Claudia and Caroline will coordinate for the conversation on ED patient navigator work. | - New templates were sent out to partners yesterday with updated columns, please reach out to Renjie if there are any questions. - Claudia and St. Mary’s can collaborate with PMO on outreach to partners who are not engaged or sending patients. - S. Choudhury will start the introductions for C. Gugliemo and C. Kean on ED patient navigatior work. |
| - DY3Q4 Deliverables: S. Choudhury/ Team | - Metric 5.3 - PMO will develop the Care coordination Roster for reporting including Peds Asthma Center, ED, Saint Mary’s nurses. - The PPS would need to engage pharmacist from the serving areas like Jackson Heights. - A current pharmacy partner is Total Care Rx , in- house pharmacy, and Alexander Infusion. - Create packet for pharmacist from DSRIP to provide to for their patients with laminated visual instructions, educational pamphlet with DSRIP referral information. - Is there a co-pay for Homecare Visit? | - Total Care Rx and Claudia would have a conversation on Asthma education. - C. Duffy will confirm whether Medicaid patients have a co-pay for homecare assessment. |
| - Questions/ Discussion: Team | - If partners are interested in Cureatr M. Hay can set up notifications with partners to be alerted when patients hit the ED. - Partner would have to submit their patient registry to be uploaded into system. - M. Hay and partners will work on configuring the tool. - H. Jabbar reported out the Education Resource Center is coming to fruition very soon and Nurses are going to be coming to educate patients. - C. Gugliemo and H. Jabbar are reviewing education tools and resources for the Education Resource Center. | - Please contact M. Hay for further information. |