|  |  |  |  |
| --- | --- | --- | --- |
| **Meeting Title:** | **NYPQ DSRIP****PCMH Project**  | **Meeting Date:** | April 4, 2017 |
| **Facilitator(s):** | M. D’Urso/ M. Cartmell | **Meeting Time:** | 10:30 PM – 11:30 PM |
| **Conference Line:** | 866-692-4538  | **Code:** | 26098085#  |
| **Location:** | NYPQ 56-45 Main Street; Radiation Oncology Room |

**Meeting Purpose:**

|  |
| --- |
| DSRIP Implementation – Project Requirements Implementation |

|  |  |  |  |
| --- | --- | --- | --- |
| **#** | **Topic** | **Responsible Person** | **Document** |
| 1. | Welcome & Purpose | M. D’Urso, RN | - |
| 2. | Approve Meeting Minutes – 03/7/17 | M. D’Urso, RN |  |
| 3.  | Project Deliverables DY2 Q4:***Status Updates on collection of following documents:*** * Care coordinator documents from PCMH partners: (CHN, Brightpoint, Rite Care, Jose Quiwa, Advanced Pediatrics, Caring Hands , NYPQ Clinics)
* EHR Workflows for care coordination from PCMH partners: (CHN, Brightpoint, Rite Care, Jose Quiwa, Advanced Pediatrics, Caring Hands , NYPQ Clinics)
* Care coordinator trackers from PCMH partners: (CHN, Brightpoint, Rite Care, Jose Quiwa, Advanced Pediatrics, Caring Hands , NYPQ Clinics)
* EHR screenshots for population health management, including use of targeted patient registries, from PCMH partners: (CHN, Brightpoint, Rite Care, Jose Quiwa, Advanced Pediatrics, Caring Hands , NYPQ Clinics)
 | M. D’Urso, RN/S.Choudhury |  |
| 4.  | **DY3 Q4 Deliverable 1:** ***Milestone# 4:*** Ensure all PPS safety net providers are actively sharing EHR systems with local health information exchange/RHIO/SHIN-NY and sharing health information among clinical partners, including direct exchange (secure messaging), alerts and patient record look up by the end of Demonstration Year (DY) 3.***Metric# 4.1***: EHR meets connectivity to RHIO’s HIE and SHIN-NY requirements.***Minimum Documentation:*** Qualified Entity (QE) participant agreements; sample of transactions to public health registries; evidence of DIRECT secure email transactions.***Metric 4.2:*** PPS uses alerts and secure messaging functionality.***Minimum Documentation:*** EHR vendor documentation; screenshots or other evidence of use of alerts and secure messaging; written training materials; list of training dates along with number of staff trained in use of alerts and secure messaging. | M. D’Urso, RN/M.Hay |  |
| 5.  | **DY3 Q4 Deliverable 2:** ***Milestone# 5:*** Ensure that EHR systems used by participating safety net providers meet Meaningful Use and PCMH Level 3 standards and/or APCM by the end of Demonstration Year 3.***Metric# 5.1***: EHR meets Meaningful Use Stage 2 CMS requirements (Note: any/all MU requirements adjusted by CMS will be incorporated into the assessment criteria).***Minimum Documentation:*** Meaningful Use certification from CMS or NYS Medicaid or EHR Proof of Certification. | M. D’Urso, RN/M.Hay |  |
| 6. | **DY3 Q4 Deliverable 3:** ***Milestone# 8***: Ensure that all staff are trained on PCMH or Advanced Primary Care models, including evidence- based preventive and chronic disease management.***Metric# 8.1:*** Practice has adopted preventive and chronic care protocols aligned with national guidelines.***Minimum Documentation:*** Policies and procedures related to standardized treatment protocols for chronic disease management; agreements with PPS organizations to implement consistent standardized treatment protocols.***Metric# 8.2:*** Project staff are trained on policies and procedures specific to evidence-based preventive and chronic disease management.***Minimum Documentation:*** Documentation of training program; written training materials; list of training dates along with number of staff trained. | M. D’Urso, RN/S.Choudhury |  |
| 7. | **DY3 Q4 Deliverable 4:** ***Milestone# 9:*** Implement open access scheduling in all primary care practices.***Metric# 9.1:*** PCMH 1A Access During Office Hours scheduling to meet NCQA standards established across all PPS primary care sites.***Minimum Documentation:*** Scheduling standards documentation; report showing third next available appointment, which could include a 1.) New patient physical, 2.) Routine exam or 3.) Return visit exam [Institute for Healthcare Improvement measures]; response times reporting; materials communicating open access scheduling; vendor system documentation; other sources demonstrating implementation.---------------------------------------------------------------- ***Metric# 9.2:*** PCMH 1B After Hours Access scheduling to meet NCQA standards established across all PPS primary care sites.***Minimum Documentation:*** Scheduling standards documentation; response times reporting; materials communicating open access scheduling; vendor system documentation; other sources demonstrating implementation.***Metric# 9.3:*** PPS monitors and decreases no-show rate by at least 15%.***Minimum Documentation:*** Baseline no-show rate with periodic reports demonstrating 15% no-show rate reduction. | M. D’Urso, RN/S.Choudhury |  |
| 8.  | Adjourn |  |  |