| Meeting Title: | NYPQ DSRIP PCMH Project | Meeting Date: | April 4, 2017 |
| --- | --- | --- | --- |
| Facilitator(s): | M. D’Urso/ M. Cartmell | Meeting Time: | 10:30 PM – 11:30 PM |
| Conference Line: | 866-692-4538 | Code: | 26098085# |
| Location: | NYPQ 56-45 Main Street; Radiation Oncology Room |  |  |

Meeting Purpose:

DSRIP Implementation – Project Requirements Implementation

| # | Topic | Responsible Person | Document |
| --- | --- | --- | --- |
| 1. | Welcome & Purpose | M. D’Urso, RN | - |
| 2. | Approve Meeting Minutes – 03/7/17 | M. D’Urso, RN |  |
| 3. | Project Deliverables DY2 Q4: Status Updates on collection of following documents: - Care coordinator documents from PCMH partners: (CHN, Brightpoint, Rite Care, Jose Quiwa, Advanced Pediatrics, Caring Hands , NYPQ Clinics) - EHR Workflows for care coordination from PCMH partners: (CHN, Brightpoint, Rite Care, Jose Quiwa, Advanced Pediatrics, Caring Hands , NYPQ Clinics) - Care coordinator trackers from PCMH partners: (CHN, Brightpoint, Rite Care, Jose Quiwa, Advanced Pediatrics, Caring Hands , NYPQ Clinics) - EHR screenshots for population health management, including use of targeted patient registries, from PCMH partners: (CHN, Brightpoint, Rite Care, Jose Quiwa, Advanced Pediatrics, Caring Hands , NYPQ Clinics) | M. D’Urso, RN/ S.Choudhury |  |
| 4. | DY3 Q4 Deliverable 1: Milestone# 4: Ensure all PPS safety net providers are actively sharing EHR systems with local health information exchange/RHIO/SHIN-NY and sharing health information among clinical partners, including direct exchange (secure messaging), alerts and patient record look up by the end of Demonstration Year (DY) 3. Metric# 4.1: EHR meets connectivity to RHIO’s HIE and SHIN-NY requirements. Minimum Documentation: Qualified Entity (QE) participant agreements; sample of transactions to public health registries; evidence of DIRECT secure email transactions. Metric 4.2: PPS uses alerts and secure messaging functionality. Minimum Documentation: EHR vendor documentation; screenshots or other evidence of use of alerts and secure messaging; written training materials; list of training dates along with number of staff trained in use of alerts and secure messaging. | M. D’Urso, RN/ M.Hay |  |
| 5. | DY3 Q4 Deliverable 2: Milestone# 5: Ensure that EHR systems used by participating safety net providers meet Meaningful Use and PCMH Level 3 standards and/or APCM by the end of Demonstration Year 3. Metric# 5.1: EHR meets Meaningful Use Stage 2 CMS requirements (Note: any/all MU requirements adjusted by CMS will be incorporated into the assessment criteria). Minimum Documentation: Meaningful Use certification from CMS or NYS Medicaid or EHR Proof of Certification. | M. D’Urso, RN/ M.Hay |  |
| 6. | DY3 Q4 Deliverable 3: Milestone# 8: Ensure that all staff are trained on PCMH or Advanced Primary Care models, including evidence- based preventive and chronic disease management. Metric# 8.1: Practice has adopted preventive and chronic care protocols aligned with national guidelines. Minimum Documentation: Policies and procedures related to standardized treatment protocols for chronic disease management; agreements with PPS organizations to implement consistent standardized treatment protocols. Metric# 8.2: Project staff are trained on policies and procedures specific to evidence-based preventive and chronic disease management. Minimum Documentation: Documentation of training program; written training materials; list of training dates along with number of staff trained. | M. D’Urso, RN/ S.Choudhury |  |
| 7. | DY3 Q4 Deliverable 4: Milestone# 9: Implement open access scheduling in all primary care practices. Metric# 9.1: PCMH 1A Access During Office Hours scheduling to meet NCQA standards established across all PPS primary care sites. Minimum Documentation: Scheduling standards documentation; report showing third next available appointment, which could include a 1.) New patient physical, 2.) Routine exam or 3.) Return visit exam [Institute for Healthcare Improvement measures]; response times reporting; materials communicating open access scheduling; vendor system documentation; other sources demonstrating implementation. ---------------------------------------------------------------- Metric# 9.2: PCMH 1B After Hours Access scheduling to meet NCQA standards established across all PPS primary care sites. Minimum Documentation: Scheduling standards documentation; response times reporting; materials communicating open access scheduling; vendor system documentation; other sources demonstrating implementation. Metric# 9.3: PPS monitors and decreases no-show rate by at least 15%. Minimum Documentation: Baseline no-show rate with periodic reports demonstrating 15% no-show rate reduction. | M. D’Urso, RN/ S.Choudhury |  |
| 8. | Adjourn |  |  |